Grant Application Approval and Submittal Process

Including Post-Award Procedures

State Center Community College District

Phase I: Initial Campus Approval and Notice of Intent to Apply

|  | Responsibility | Action |
| --- | --- | --- |
| Step 1 | Initiator | Obtain grant information and/or Request for Applications (RFA), and discuss concept with appropriate supervisor, manager or dean. |
| Step 2 | Initiator | Follow Reedley College’s internal steps as follows: - Complete Permission to Apply, Grant Application/Report - Attach brief abstract/summary along with preliminary budget - Route for signatures |
| Step 3 | Initiator | One month prior to deadline: Complete on-line NOI form found on the grants office page of the SCCCD Intranet site. (http://intranet.scccd.net/GrantsOffice/) |
| Step 4 | President | Via e-mail, each President/Vice Chancellor receives the NOIs for the campus with an approve/decline option. - Approve the NOI: Webmaster will receive an automated notice to send the NOI as a District-wide mail-all. - Decline to approve the NOI: Initiator will receive an automated notice to contact the President for further instructions |
| Step 5 | District Webmaster | Send all approved NOI forms as District-wide mail-alls within one week of receiving approval notice. |

Phase II: Grant Preparation and Submittal*

|  | Responsibility | Action |
| --- | --- | --- |
| Step 1 | Supervisor, Manager, Dean, or Vice President | Identify grant manager or project director, and identify campus grant writer to work with the Director, Grants and External Funding to prepare the grant application. NOTE: The content and accuracy of the information contained in the grant proposal are the sole responsibility of the area administrator and assigned staff/faculty member. |
| Step 2 | Campus grant writer | 15 days prior to deadline: Consult with Director of Grants and External Funding for assistance. Consult with Dean, Human Resources, Director of the Personnel Commission and/or Legal Council as needed. |
| Step 3 | Campus grant writer | 10 days prior to deadline: Submit complete draft to appropriate supervisor, manager or dean for review and input. |
| Step 4 | Campus grant writer | After approval from supervisor, submit application to the Director of Grants and External Funding for review and input. |
| Step 5 | Campus grant writer | 10 days prior to deadline: Submit complete budget, including matching funds if required, to campus business office for review and approval. |
| Step 6 | Campus Business Office | 5 days prior to deadline: Submit approved budget to District Office Accountant/Auditor for review and approval. |
| Step 7 | D.O. Accountant/Auditor | Forward approved budget to the Director, Grants and External Funding. |
| Step 8 | Campus grant writer | 3 days prior to deadline: Work with Director, Grants and External Funding to compile final document. Submit to VP, Administrative Services, Area VP and President for final approval (signed transmittal form.) Forward the signed form to the Director, Grants and External Funding. NOTE: Grant proposals will NOT be signed/submitted by the District Office unless signed approvals are provided by the campus. |
| Step 9 | Accountant/Auditor | When final application with campus approvals is received, obtain final sign-off of Vice Chancellor, Finance and Administration or other authorized designee. |
| Step 10 | Director/Grants and External Funding | Work with campus grant writer to prepare/submit application. Create/distribute copies of submitted grant for the campus Business Office and the project director. *See last page of this section for information on electronic submittals via www.grants.gov |

Phase III: Post-Grant Award and Project Implementation

|  | Responsibility | Action |
| --- | --- | --- |
| Step 1 | Project director/campus grant writer | Send copies of notification of award or denial of the grant to: Campus Administration and Finance Department, area Dean or responsible administrator, and District Director of Grants and External Funding. The executed grant agreement will be sent to the District Office of Finance and Administration. |
| Step 2 | District Office of Finance and Administration | Provide copies of executed grant agreement documents to the college Business Manager and the District Office of Grants and External Funding. |
| Step 3 | District Accounting Manager | Prepare an agenda item accepting the grant for approval by the SCCCD Board of Trustees. As needed, provide a copy of resolution or minutes to the campus responsible administrator. |
| Step 4 | Area Dean or VP | Appoint a project director to assume responsibility for day-to-day operations, monitoring and oversight of the grant. This may or may not be the grant writer. |
| Step 5 | Project Director | Work with campus Finance and Administration Office to develop a detailed project budget and submit to the District Accountant/Auditor to assign categorical funding account numbers. |
| Step 6 | Project Director | Consult with District Personnel Office and complete MAGIC forms for the funded positions in the grant. |
| Step 7 | Project Director, Area Dean or responsible administrator | Hire or assign other grant funded personnel, set up program recordkeeping and reporting system. The District Office of Grants and External Funding will provide the Grant Policy and Procedure Manual as a guide for project management and recordkeeping. NOTE: Project Directors at the campuses are responsible for knowing and complying with reporting requirements and deadlines. Fiscal reports must be reviewed by the campus business offices and the District Accountant Auditor prior to submission. |

*Electronic Submittals via www.grants.gov

|  | Responsibility | Action |
| --- | --- | --- |
| Step 1 | Director/Grants and External Funding | Download RFA and application packet information from www.grants.gov. |
| Step 2 | ALL | Follow grant preparation and approval processes as described in Phase II above. |
| Step 3 | Director/Grants and External Funding, | Upload narratives and required forms into the grants.gov system. Grant initiator should be available to confirm any revisions prior to upload. NOTE: The content and accuracy of the information contained in the grant proposal are the sole responsibility of the area administrator and assigned staff/faculty member. |
| Step 4 | Director/Grants and External Funding, | Inputs approved budget into grants.gov budget forms. |
| Step 6 | Administrator named on grants.gov face sheet (424 form) | Receives three levels of confirmation e-mail: - Grants.gov has received application - Application packet is complete - Packet has been forwarded to funding agency If any of these e-mails are not received, or indicate that there is an issue with the application, the Director of Grants & External Funding should be notified immediately. |
| Step 7 | Director/Grants and External Funding | Creates/distributes copies of final grant for the campus Business Office and the Project Director. |